| Year One Program Deliverables | Progress Highlights | Emerging Themes | Year Two Goals & Deliverables |
| --- | --- | --- | --- |
| Develop Connecticut’s Maritime Workforce Activities Proposed: - Develop a training environment in Connecticut that supports the needs of the maritime cluster. - Provide ABYC training and certification to 25 graduates of Connecticut’s two marine vocational schools. - Provide ABYC training and certification to 20 Connecticut marina employees. - Provide course curriculum and industry representation for developing the third vocational marine magnet school in Southeastern Connecticut. - Work with the Workforce Investment Board to train inner city workers for port related career occupations. - Introduce the maritime career fields to high school students through the Connecticut school to career program and other state educational initiatives and programs. | - Received a $52,000 grant from SECT WIB, which was used to train 160 port workers in New London, New Haven and Bridgeport. - Implemented Maritime Education Working Group. Two-year marine technician certification course under early development with the Sound School and Gateway Community College. Develop the curriculum to exceed ABYC industry standards utilizing the state’s educational infrastructure. - Developing the “Connecticut Maritime Foundation” as a resource for industry education needs. - Industry Contribution to this deliverable: $10,000 cash funding and 38 executive hours over 4 working sessions totaling $3,800 of in-kind services focused on this deliverable. Industry contributed an additional $132,000 in-kind to train deep-water port employee. | - Critical shortage of industry workers with appropriate technical and entrepreneurial skills. - Cluster members willing to participate with education to expand industry-education partnerships. - Pursue adoption of maritime technician and other certificate programs with community colleges and education/training providers. - Pursue additional funding for training programs. | Maritime Workforce Infrastructure. Prioritized deliverables to meet stated goal: - Develop a pilot marine technology certification program between The Sound School and Gateway Community College. - Develop internships and mentoring between maritime businesses and maritime training providers. - Strengthen relationships with the Workforce Investment Boards to continue upgrading the skill level of Connecticut’s maritime workforce. Develop the “Connecticut Maritime Foundation” as a recipient for federal industry educational grants. - Provide industry assistance to design system and programs that increase awareness of maritime careers. |